## RMS
Screen/Function | Description |  | In Charge | Priority | SMS | Status | Notes | Change
Home Page | Home Page: As a guest user, I want to view promotions, bestsellers, and new drinks so that I can quickly see the latest offers and featured products. | DucNV |  | 1 | II.2.1.1 | Done
User Register | Allows new customers to create an account by providing basic information (name, email, password). | DucNV |  | 1 | II.2.2.1 | Done | Check độ dài tên, sau đăng kí gửi 1 mail accpet về mail của người đăng kí (Đã thêm) | Đã có check, có gửi mail (gửi về 1 captcha)
User Login | Allows customers to sign in with their registered email/username and password to access their account on the coffee shop website | AnhNQ |  | 1 | II.2.2.2 | Done |  | Đã thêm Google login
Blank Dashboard |  | AnhNQ |  | 1 |  | Done |  | Đã gộp header footer navbar
Password Reset | If customers forget their password, they can enter their registered email. The system will send a reset link or OTP to create a new password. | AnhNQ |  | 1 | II.2.2.3 | Done | Gửi OTP về cho email nhập gồm đoạn mã 6 ký tự
User List | Show all user has register and display key details such as ID user, Name, Email, role, address, phone | AnhNQ |  | 1 | II.2.3.1.2 | Done
New User | Allows HR to create new user including name, gmail, role, and password | AnhNQ |  | 1 | II.2.3.1.3 | Done
User Details | Shows customer info (name, email,...). Customers can view or update their details. | AnhNQ |  | 1 | II.2.3.1.5 | Done
Product List | Display all product with key details such as product ID, name, image, price, status... | MinhNC |  | 1 | II.2.3.2.3 | Done | Chưa có sắp xếp | Đã có sắp xếp theo cột
New Product | Allow maketer to add new product including name, product ID, image, price | MinhNC |  | 1 | II.2.3.2.2 | Done | Thông báo không dùng PoolUp, chỉnh lại UI dùng control khác có text area
Product Details | Show all product details can be edited by maketer including image, ID, name, price, and description | MinhNC |  | 1 | II.2.3.2.4 | Done | Cần upload ảnh chứ không lấy link | đã chuyển sang upload ảnh
Setting List | Setting List: As an admin, I want to view, search, and manage system settings so that I can configure business operations such as opening hours, delivery fees, VAT, and notifications. |  | x | 1 | II.2.3.5.2 | Done
New Setting |  |  | x
Setting Details | Setting Details: As an admin, I want to view and update detailed information of a specific setting so that I can manage system configurations accurately. |  | x | 1 | II.2.3.5.3 | Done
Promotion List | Displays all promotions with key information such as title, discount type, value, duration, and status. Admin or Marketer can view, search, and manage promotions easily. | MinhNC |  | 1 |  | Done | Chưa có sắp xếp
New Promotion | New Promotion delivers exclusive, limited-time perks designed to maximize customer value. Act quickly to enjoy these special benefits before the offer expires. | MinhNC |  |  |  |  | Thông báo không dùng PoolUp, chỉnh lại UI dùng control khác có text area
Promotion Details | Shows detailed information of a specific promotion and allows editing or updating its content and status. | MinhNC |  | 1 |  | Done
Public Products | Public Products: As a guest user, I want to browse, search, and filter products by category or price so that I can easily find items I am interested in. | MinhNC |  |  | II.2.1.2 | Done
Public Product Details | Public Product Details: As a guest user, I want to view detailed information about a product, including description, size, and price, so that I can decide whether to add it to my cart or buy it immediately. | MinhNC |  |  | II.2.1.3 | Done
Public Promotions | Public Promotions showcases wide-reaching offers crafted to engage and reward every customer. Explore the latest deals and seize limited-time savings before they’re gone. | MinhNC |  |  |  | Done
My Profile | A personal page where customers can view and update their details, such as name, email, role and default delivery address for coffee orders. | AnhNQ |  |  | II.2.2.6 | Done |  | Đã có thêm phone và address được lấy từ db
Password Change | Enables logged-in customers to change their password by entering the old password and setting a new one. | AnhNQ |  |  | II.2.2.7 | Done |  | Update password của user và sửa vào db
My Orders | Displays a list of all coffee orders placed by the customer, including order number, order date, total amount, and current status (e.g., Pending, Preparing, Out for Delivery, Completed, or Cancelled). |  |  | 3 | II2.2.4 | Done
My Order Details | Shows detailed information for a specific coffee order, including product names (coffee drinks, beans, or pastries), quantity, price breakdown, delivery address, payment method. |  |  | 3 | II.2.2.5 | Done
Shopping Cart | Shopping Cart: As a customer, I want to view, update, or remove items in my cart so that I can review my order and proceed to checkout with the correct products and quantities. |  |  |  | II.2.1.4 | Done
Order List | Shows all customer orders with key details such as order ID, customer name, order date, total amount, and status. | DucNV |  |  |  | Done
New Order | Allows staff to create a new customer order manually (e.g., in-store orders, phone orders, or special requests). | DucNV |  |  | II.2.3.3.3 | Done
Cashier Dashboard | Displays recent orders (10 orders), customer orders with key details such as order code, total amount, total payment (paid), creation date, current status. Basic statistics include total orders, total orders of each type (Completed, pending, cancelled) and revenue (10 orders displayed) | DucNV |  |  | II.2.3.3.1 | Done
Order Details/ (Edit order pending) | Provides information (Products, unit price, total price, price payable) about a specific order. Allows staff to edit products in the order if the order is in Pending status. | DucNV |  |  | II.2.3.3.2 | Done
API PAYOS | THANH TOÁN TIỀN MẶT VÀ PAYOS (PayOs thì đki rồi lấy api) |  |  |  |  | Done

## Copy of RMS
Screen/Function | Description |  | In Charge | Priority | SMS | Status | Notes | Change
Home Page | Home Page: As a guest user, I want to view promotions, bestsellers, and new drinks so that I can quickly see the latest offers and featured products. | DucNV |  | 1 | II.2.1.1 | Done
User Register | Allows new customers to create an account by providing basic information (name, email, password). | DucNV |  | 1 | II.2.2.1 | Done | Check độ dài tên, sau đăng kí gửi 1 mail accpet về mail của người đăng kí (Đã thêm) | Đã có check, có gửi mail (gửi về 1 captcha)
User Login | Allows customers to sign in with their registered email/username and password to access their account on the coffee shop website | AnhNQ |  | 1 | II.2.2.2 | Done
Blank Dashboard |  | AnhNQ |  | 1 |  | Done
Password Reset | If customers forget their password, they can enter their registered email. The system will send a reset link or OTP to create a new password. | AnhNQ |  | 1 | II.2.2.3 | Done
User List | Show all user has register and display key details such as ID user, Name, Email, role... | KhaiLT |  | 1 | II.2.3.1.2 | Done
New User | Allows HR to create new user including name, gmail, role, and password | KhaiLT |  | 1 | II.2.3.1.3 | Done
User Details | Shows customer info (name, email,...). Customers can view or update their details. | KhaiLT |  | 1 | II.2.3.1.5 | Done
Product List | Display all product with key details such as product ID, name, image, price, status... | MinhNC |  | 1 | II.2.3.2.3 | Done | Chưa có sắp xếp | Đã có sắp xếp theo cột
New Product | Allow maketer to add new product including name, product ID, image, price | MinhNC |  | 1 | II.2.3.2.2 | Done | Thông báo không dùng PoolUp, chỉnh lại UI dùng control khác có text area
Product Details | Show all product details can be edited by maketer including image, ID, name, price, and description | MinhNC |  | 1 | II.2.3.2.4 | Done | Cần upload ảnh chứ không lấy link | đã chuyển sang upload ảnh
Setting List | Setting List: As an admin, I want to view, search, and manage system settings so that I can configure business operations such as opening hours, delivery fees, VAT, and notifications. | DaiND | x | 1 | II.2.3.5.2 | Done
New Setting |  | DaiND | x
Setting Details | Setting Details: As an admin, I want to view and update detailed information of a specific setting so that I can manage system configurations accurately. | DaiND | x | 1 | II.2.3.5.3 | Done
Promotion List | Displays all promotions with key information such as title, discount type, value, duration, and status. Admin or Marketer can view, search, and manage promotions easily. | MinhNC |  | 1 |  | Done | Chưa có sắp xếp
New Promotion | New Promotion delivers exclusive, limited-time perks designed to maximize customer value. Act quickly to enjoy these special benefits before the offer expires. | MinhNC |  |  |  |  | Thông báo không dùng PoolUp, chỉnh lại UI dùng control khác có text area
Promotion Details | Shows detailed information of a specific promotion and allows editing or updating its content and status. | MinhNC |  | 1 |  | Done
Public Products | Public Products: As a guest user, I want to browse, search, and filter products by category or price so that I can easily find items I am interested in. | MinhNC |  |  | II.2.1.2 | Done
Public Product Details | Public Product Details: As a guest user, I want to view detailed information about a product, including description, size, and price, so that I can decide whether to add it to my cart or buy it immediately. | MinhNC |  |  | II.2.1.3 | Done
Public Promotions | Public Promotions showcases wide-reaching offers crafted to engage and reward every customer. Explore the latest deals and seize limited-time savings before they’re gone. | MinhNC |  |  |  | Done
My Profile | A personal page where customers can view and update their details, such as name, email, role and default delivery address for coffee orders. | AnhNQ | x |  | II.2.2.6 | Done
Password Change | Enables logged-in customers to change their password by entering the old password and setting a new one. | AnhNQ |  |  | II.2.2.7 | Done
My Orders | Displays a list of all coffee orders placed by the customer, including order number, order date, total amount, and current status (e.g., Pending, Preparing, Out for Delivery, Completed, or Cancelled). | DaiND |  | 3 | II2.2.4 | Done
My Order Details | Shows detailed information for a specific coffee order, including product names (coffee drinks, beans, or pastries), quantity, price breakdown, delivery address, payment method. | DaiND |  | 3 | II.2.2.5 | Done
Shopping Cart | Shopping Cart: As a customer, I want to view, update, or remove items in my cart so that I can review my order and proceed to checkout with the correct products and quantities. | KhaiLT |  |  | II.2.1.4 | Done
Order List | Shows all customer orders with key details such as order ID, customer name, order date, total amount, and status. | DucNV |  |  |  | Done
New Order | Allows staff to create a new customer order manually (e.g., in-store orders, phone orders, or special requests). | DucNV |  |  | II.2.3.3.3 | Done
Cashier Dashboard | Displays recent orders (10 orders), customer orders with key details such as order code, total amount, total payment (paid), creation date, current status. Basic statistics include total orders, total orders of each type (Completed, pending, cancelled) and revenue (10 orders displayed) | DucNV |  |  | II.2.3.3.1 | Done
Order Details/ (Edit order pending) | Provides information (Products, unit price, total price, price payable) about a specific order. Allows staff to edit products in the order if the order is in Pending status. | DucNV |  |  | II.2.3.3.2 | Done
Order Checkout | THANH TOÁN TIỀN MẶT VÀ PAYOS (PayOs thì đki rồi lấy api) | KhaiLT |  |  |  | Done
API SCM |  |  | x |  |  | To Do

## Sheet1
Use Case | Description | Level | LOC | In Charge | Done-In | RDS | Status | Updated | Update Details
Login | As any role I want to log in to access the sales and marketing system | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Logout | As any role I want to log out to securely end my session | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Product List | As Customer or Staff I want to see all available products | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Product Detail | As Customer or Staff I want to see detailed information for each product | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Search Product by Name | As Customer or Staff I want to search products by name | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Create Order | As Customer I want to place an order for products | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View My Orders | As Customer I want to see all my past and current orders | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Order Details | As Customer I want to see complete order information | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Search Product by Code | As Staff I want to search products by SKU/barcode | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Filter Product by Category | As Customer or Staff I want to filter products by category | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Filter Product by Price Range | As Customer I want to filter products by price range | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Add New Product | As Admin I want to add new products to the catalog | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Edit Product Information | As Admin I want to update product details price images | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Product Inventory | As Sales Staff I want to check product availability/stock | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Change My Password | As any role I want to change my own password | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Edit My Profile | As any role I want to update my own profile information | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Low Stock Alerts | As Manager I want to see which products are running low | 2 |  |  | Iteration 2 | Y | Done | Not Yet
View All Orders | As Sales Staff I want to see all customer orders | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Search Orders | As Sales Staff I want to search orders by customer name or order ID | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Filter Orders by Status | As Sales Staff I want to filter orders by status (Pending Processing Completed Cancelled) | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Update Order Status | As Sales Staff I want to update order processing status | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Cancel Order | As Customer or Sales Staff I want to cancel an order | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Edit Order | As Sales Staff I want to modify order items before confirmation | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Add Product to Cart | As Customer I want to add products to shopping cart | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Shopping Cart | As Customer I want to see items in my cart | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Update Cart Quantity | As Customer I want to change product quantity in cart | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Remove from Cart | As Customer I want to remove items from cart | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Apply Promotion Code | As Customer I want to apply discount codes at checkout | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Checkout | As Customer I want to complete purchase and place order | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Select Payment Method | As Customer I want to choose payment method (Cash Card E-wallet) | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Process Payment | As Sales Staff I want to process customer payment | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Payment History | As Customer I want to see my payment records | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View All Payments | As Sales Staff or Manager I want to see all payment transactions | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Generate Invoice | As Sales Staff I want to generate receipt/invoice for customer | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Active Promotions | As Customer I want to see current promotions and discounts | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Create Promotion | As Marketing Staff I want to create new promotional campaigns | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Edit Promotion | As Marketing Staff I want to update promotional details | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View All Promotions | As Marketing Staff or Manager I want to see all promotion campaigns | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Search Promotions | As Marketing Staff I want to search promotions by name or code | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Activate/Deactivate Promotion | As Marketing Staff I want to enable or disable promotions | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Promotion Performance | As Manager I want to see promotion effectiveness statistics | 2 |  |  | Iteration 2 | Y | Done | Not Yet
Register Account | As Customer I want to create an account | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Customer List | As Sales Staff or Manager I want to see all registered customers | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Search Customers | As Sales Staff I want to search customers by name or email | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Customer Details | As Sales Staff I want to see customer profile and purchase history | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Filter Customers | As Sales Staff I want to filter customers by status or purchase amount | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Edit Customer Info | As Admin I want to update customer information | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Deactivate Customer | As Admin I want to deactivate customer account | 1 |  |  | Iteration 1 |  | To Do | Not Yet
View User List | As Admin I want to see all system users (Staff Manager Admin) | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Add User | As Admin I want to create new staff accounts | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Edit User Information | As Admin or HR I want to update user status or role | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Search Users | As Admin I want to search users by name or email | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Filter Users by Role | As Admin I want to filter users by their role | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Deactivate User | As Admin I want to deactivate user accounts | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Categories | As Customer or Staff I want to see all product categories | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Create Category | As Admin I want to add new product categories | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Edit Category | As Admin I want to update category information | 1 |  |  | Iteration 1 | Y | Done | Not Yet
Delete Category | As Admin I want to remove categories | 1 |  |  | Iteration 1 | Y | Done | Not Yet
View Sales Dashboard | As Manager I want to see sales overview and statistics | 2 |  |  | Iteration 2 | Y | Done | Not Yet
View Sales by Product | As Manager I want to see which products sell best | 2 |  |  | Iteration 2 | Y | Done | Not Yet
View Sales by Date | As Manager I want to see daily/weekly/monthly sales reports | 2 |  |  | Iteration 2 | Y | Done | Not Yet
View Revenue Report | As Manager I want to see revenue breakdown and trends | 2 |  |  | Iteration 2 | Y | Done | Not Yet
Export Sales Report | As Manager I want to export reports to Excel | 2 |  |  | Iteration 2 | Y | Done | Not Yet
View Customer Analytics | As Marketing Staff I want to see customer behavior statistics | 2 |  |  | Iteration 2 | Y | Done | Not Yet
View System Settings | As Admin I want to manage system configuration | 2 |  |  | Iteration 2 | Y | Done | Not Yet
Update Company Info | As Admin I want to update company/branch information | 2 |  |  | Iteration 2 | Y | Done | Not Yet
Manage Tax Settings | As Admin I want to configure tax rates | 2 |  |  | Iteration 2 | Y | Done | Not Yet
View Activity Logs | As Admin I want to see system activity and user actions | 2 |  |  | Iteration 2 | Y | Done | Not Yet